## Project Summary
Project Summary — Sample: Wind Farm, Tirunelveli, Tamil Nadu
Parameter | Value / Specification | Notes / Remarks
Project Information
Project Name | Muppandal Wind Farm Extension — Phase III
Developer | Renewable Energy Corp. Ltd.
Project Location | Muppandal Village, Tirunelveli District, Tamil Nadu
Site Coordinates | 8.7134°N, 77.6321°E (WGS 84) | Approximate center of wind farm
Site Elevation | Approx. 180 m above MSL | Arid plateau terrain
Nearest Town | Tirunelveli (35 km) | For logistics and accommodation
Nearest Airport | Thoothukudi Airport (90 km) | For equipment transport
Access Road | SH-154 + 2 km unpaved approach road | Need improvement for heavy vehicles
Land Ownership | Government poramboke land + private lease | Clearance status pending
Mast Specification Requirements
Mast Type | Guyed Lattice Tower | Self-supporting not feasible due to foundation cost
Mast Height | 120 m | To match proposed turbine hub height (120-140m)
Proposed Turbine | Vestas V150-4.5 MW / Envision EN-171-5.0 | Hub height 120-140m
Number of Masts | 2 (this procurement: 1 no.) | Second mast for sector-wise correlation
Measurement Duration | 24 months minimum | Per IEC 61400-12-1 for bankable assessment
Data Recovery Target | ≥ 90% over 12-month periods | Industry standard for bankability
Site Environmental Conditions
Wind Zone (IS 875-3) | Zone IV — Basic Wind Speed Vb = 47 m/s | Tamil Nadu coastal/inland
Terrain Category (IS 875-3) | Category 2 — Open terrain with scattered obstructions | Plateau with sparse vegetation
Design Wind Speed (50-yr return) | To be computed per IS 875-3 with K1, K2, K3, K4 factors | Vendor to compute and certify
Maximum Recorded Wind Speed | Approx. 45 m/s (from nearby IMD station) | Historical data from Nagercoil IMD
Cyclone Risk | Moderate — eastern coast of Tamil Nadu | Cyclone tracks from Bay of Bengal
Temperature Range | 20°C to 42°C | Hot arid climate
Annual Rainfall | 600-800 mm (NE monsoon dominant) | Oct-Dec heavy rain period
Humidity Range | 40% to 90% | Coastal influence
Lightning Incidence | High — 20-30 thunderstorm days/year | IS 2309 / IEC 62305 Level II-III
Corrosion Environment | Moderate — 40 km from coast, arid inland | Not severe marine but salt dust possible
Seismic Zone (IS 1893) | Zone III (Moderate) | Tirunelveli district
Soil Type | Medium clay / weathered rock at 2-3m depth | Based on preliminary geotech
Safe Bearing Capacity | 150 kN/m² (assumed, pending soil test) | To be confirmed by soil investigation
Ground Water Table | 5 m below GL (seasonal variation ±2m) | Monsoon water table rise
Site Topography | Complex terrain — ridgeline plateau with moderate relief | Affects flow modelling approach
Regulatory Requirements
Aviation Clearance | NOC required from AAI for height > 60m | Mast is 120m — mandatory
Aviation Light | Low-intensity Type A red flashing light per ICAO | DGCA requirement
Aviation Painting | Alternate orange/white bands per AAI guidelines | Entire mast height
Forest Clearance | Not applicable — non-forest land | To be confirmed
Environmental Clearance | Not required for temporary met mast (< 5 years) | MoEFCC exemption
Local Body Permission | Panchayat NOC required | To be obtained by developer
Project Timeline
RFP Issue Date | 15-Jul-2026
Bid Submission Deadline | 15-Aug-2026
Technical Evaluation | Aug 2026 (2 weeks)
Commercial Evaluation | Aug 2026 (1 week)
Purchase Order | 01-Sep-2026
Fabrication Period | 8-10 weeks from PO | Vendor to confirm
Delivery to Site | Nov 2026 | Before NE monsoon peak
Erection & Commissioning | Dec 2026 (target) | Weather window critical
Data Collection Start | 01-Jan-2027 | 24-month campaign

## Mast Structure
Mast Structure — Procurement Checklist
# | Category | Item | What to Ask the Vendor / Specification | Standard / Reference | Priority | Vendor Response | Compliant? | Remarks
1 | 1. General & Design Standards | Mast type confirmation | Confirm mast type: guyed lattice vs self-supporting. For 120m, guyed lattice is standard and cost-effective. Self-supporting requires massive foundation and is 3-4x costlier. | IEC 61400-12-1 §5.1 | Critical
2 |  | Mast height confirmation | Confirm mast height: 120m above ground level (AGL). Height must match or exceed proposed turbine hub height. For 140m hub height turbines, consider 120m mast with reliable vertical extrapolation. | IEC 61400-12-1 | Critical
3 |  | Design code compliance | Confirm structural design complies with IS 875 (Part 3) for wind loads, IS 1893 for seismic loads, and BS EN 1993-3-1 for steel lattice towers. Ask for compliance certificate. | IS 875-3 / IS 1893 / BS EN 1993-3-1 | Critical
4 |  | IEC 61400-12-1 compliance | Confirm the complete mast setup (structural + instrumentation boom mounting locations) is designed to comply with IEC 61400-12-1 for wind measurement. This is critical for data bankability. | IEC 61400-12-1 | Critical
5 |  | Design life | Specify minimum 20-year structural design life. Ask vendor to confirm design life and provide fatigue analysis if site has high vibration. | IS 875-3 / Industry Practice | High
6 |  | Third-party design review | Require that structural design is reviewed and certified by an independent qualified structural engineer (not the vendor's own engineer). Ask for the reviewer's credentials. | Industry Best Practice | Critical
1 | 2. Wind & Environmental Loading | Design wind speed | Ask vendor to compute design wind speed per IS 875-3: Vd = Vb × K1 × K2 × K3 × K4. For Tirunelveli Zone IV: Vb=47 m/s, K1=1.06 (important structure), K2=1.05 (120m height), K3=1.0 (topography), K4=1.15 (cyclone-prone). Ask for design calculations. | IS 875-3 | Critical
2 |  | Survival wind speed | Ask: What is the survival wind speed of the mast? Should be at least 1.3× the 50-year return period 3-second gust speed. For this site, survival wind speed should be ≥ 65 m/s. | IS 875-3 / IEC 61400-12-1 | Critical
3 |  | Cyclone resistance | Ask: Is the mast designed for cyclonic wind speeds? Tamil Nadu east coast is cyclone-prone. Vendor must demonstrate cyclone-resistant design with K4 factor as per IS 875-3. | IS 875-3 §6.3.3 | Critical
4 |  | Ice loading design | Ask: Has ice loading been considered? For Tamil Nadu site, ice is not a concern, but vendor should confirm ice load = 0 is acceptable. If site were in Himalayan region, radial ice of 25-50mm would be needed. | IS 875-3 / BS EN 1991-1-3 | Medium
5 |  | Seismic loading | Ask: Has seismic loading been considered per IS 1893? For Zone III (Tirunelveli), seismic coefficient Ah = (Z/2) × (I/R) × (Sa/g). Vendor must provide seismic design calculations for mast + foundation. | IS 1893:2016 | High
6 |  | Temperature loading | Ask: Has thermal expansion been considered? Steel expands ~12mm per 100m per 10°C. For 120m mast with 22°C temperature range, expansion can be ~30mm. Ask for expansion joint design. | BS EN 1991-1-5 | Medium
7 |  | Guy wire dynamic response | Ask: Has guy wire vibration (galloping, aeolian vibration) been analyzed? Ask for dynamic analysis of guy wire system including damping measures. | BS EN 1993-3-1 | High
8 |  | Wind direction loading | Ask: Has the mast been designed for wind loading from all 360° directions? IEC requires measurement from all directions, so the mast must survive wind from any direction. | IS 875-3 | High
1 | 3. Structural Members & Sections | Main leg specification | Ask: What is the main leg section? Typical: ISA 80×80×8 or ISA 90×90×10 angle. Ask for section properties, grade of steel (minimum E250 per IS 2062), and slenderness ratio check. | IS 806 / IS 2062 | Critical
2 |  | Bracing members | Ask: What are the bracing member sections? Typically ISA 50×50×6 or ISA 60×60×6 for horizontal/diagonal bracings. Confirm all members are designed as per IS 800. | IS 800 | High
3 |  | Steel grade | Specify: Minimum Grade E250 (Fe 410W) per IS 2062. For critical connections and high-stress members, consider E300 (Fe 490). Ask for mill test certificates for all steel. | IS 2062 Grade E250 | Critical
4 |  | Face width of mast | Ask: What is the mast face width? Typical for 120m guyed lattice: 1.2m to 1.5m square. This directly affects anemometer boom length requirement (min 6× face width). | IEC 61400-12-1 | Critical
5 |  | Member connection type | Ask: Are connections bolted or welded? Prefer bolted connections for field assembly. All HSFG bolts per IS 4000. Avoid site welding — difficult to control quality. | IS 4000 / IS 800 | High
6 |  | Base plate design | Ask: What is the base plate size and thickness? Typically 400×400×20mm or larger with 4 anchor bolts. Ask for base plate design calculations. | IS 800 | High
7 |  | Anchor bolt specification | Ask: What are the anchor bolt specifications? Typically M30 or M36 Grade 8.8, galvanized, with embedment length as per IS 456. Minimum 4 anchor bolts. Ask for pull-out calculations. | IS 456 / IS 1363 | Critical
8 |  | Section drawings | Ask vendor to provide detailed section drawings showing all member sizes, connection details, and boom mounting locations at each measurement height. | Industry Practice | High
1 | 4. Guy Wire System | Guy wire specification | Ask: What is the guy wire specification? Should be galvanized steel wire rope per IS 2266. Typical: 20mm or 22mm diameter, 6×37 or 1×37 construction. Ask for breaking load certificate. | IS 2266 | Critical
2 |  | Guy wire configuration | Ask: How many guy wire levels? For 120m mast: typically 4 levels (at 30m, 60m, 90m, 120m) with 4 wires per level (90° apart). Ask for guy wire layout drawing. | Industry Practice | Critical
3 |  | Guy wire tensioning | Ask: What is the specified guy wire pre-tension? Typically 8-12% of breaking load. Ask for tensioning procedure and equipment (come-along clamps, load cells). Tension must be checked after erection. | Industry Practice | High
4 |  | Turnbuckles | Ask: Are turnbuckles provided for tension adjustment? Specify: galvanized, forged steel, jaw-jaw or jaw-eye type per IS 4211. Size should match guy wire diameter. Ask for proof load certificates. | IS 4211 | High
5 |  | Guy anchor design | Ask: How are guy anchors designed? For 150 kN/m² SBC soil: typical guy anchor is 1.5m × 1.5m × 1.2m concrete block with U-bolt eye. Ask for pull-out calculation based on actual soil parameters. | IS 1904 / BS EN 1997 | Critical
6 |  | Guy anchor distance | Ask: What is the guy anchor distance from mast base? Typically 60-80% of guy attachment height. For 120m mast with 4 levels: anchors at 35-50m from base. Ask for guy geometry drawing. | Industry Practice | High
7 |  | Guy wire insulators | Ask: Are guy wire insulators (break-up insulators) provided? These prevent guy wires from resonating with radio frequencies and reduce aeolian vibration. At least 2 per wire. | IEC 62305 / Industry Practice | Medium
8 |  | Safety factor for guys | Ask: What is the safety factor for guy wires? Minimum 2.5 against breaking load as per IS 802. Ask for guy wire load calculation with all load combinations. | IS 802 | Critical
1 | 5. Hot-Dip Galvanizing | Galvanizing standard | Specify: All structural steel members MUST be hot-dip galvanized per IS 2629 and IS 2633. No paint-only corrosion protection. Galvanizing is mandatory for long-term durability. | IS 2629 / IS 2633 | Critical
2 |  | Minimum zinc coating thickness | Specify: Minimum zinc coating thickness of 86 microns (610 g/m²) for members ≤ 5mm thick, and 98 microns (700 g/m²) for members > 5mm thick per IS 2629 Table 1. Ask vendor to confirm and provide test certificates. | IS 2629 Table 1 | Critical
3 |  | Zinc grade | Specify: Zinc used for galvanizing shall be minimum Grade Zn 98 per IS 209. Ask for zinc certificate of conformity. | IS 209 | High
4 |  | Surface preparation | Ask: What surface preparation is done before galvanizing? Must include degreasing, acid pickling (HCl 10-15%), fluxing (zinc ammonium chloride), and drying per IS 2629. No blast cleaning alone. | IS 2629 §4 | High
5 |  | Galvanizing bath temperature | Ask: What is the galvanizing bath temperature? Should be 440-460°C per IS 2629. Over-temperature causes brittle Fe-Zn alloy layers. Ask for bath temperature records. | IS 2629 | High
6 |  | Dipping time | Ask: What is the typical dipping time? For structural angles: 4-8 minutes per IS 2629. Under-dipping = thin coating; over-dipping = thick but brittle coating. Ask for process records. | IS 2629 | Medium
7 |  | Centrifuging for small parts | Ask: Are small parts (bolts, nuts, washers, clips) centrifuged after galvanizing to remove excess zinc? Required per IS 2629 §5.3. Prevents thread clogging and ensures proper fit. | IS 2629 §5.3 | High
8 |  | Thread protection | Ask: How are galvanized bolt threads protected? Oversize tapping of nuts per IS 1363 Part 3 is standard. Threads must be clean and free of zinc runs. Ask for thread gauge check procedure. | IS 1363 Part 3 | High
9 |  | Repair of damaged galvanizing | Ask: What is the procedure for repairing damaged galvanizing (transport/erection damage)? Must use zinc-rich paint per IS 2629 §6 with minimum 92% zinc in dry film. Ask for repair procedure documentation. | IS 2629 §6 | High
10 |  | Galvanizing test certificates | Require: Zinc coating thickness test certificates per IS 2633 for each batch. Test method: magnetic thickness gauge (IS 6932) or gravimetric method (IS 2633). Ask for sample test reports. | IS 2633 / IS 6932 | Critical
11 |  | Adhesion test | Ask: Is adhesion testing performed per IS 2629? Pali knife test or bend test to confirm zinc-steel bond. No peeling or flaking acceptable. | IS 2629 §7 | High
12 |  | Uniformity test | Ask: Is uniformity of coating tested per IS 2633 using copper sulfate immersion test (Preece test)? Minimum 4 dips without copper deposition on base metal. | IS 2633 §5 | High
13 |  | Appearance | Specify: Galvanized surface shall be smooth, continuous, and free from bare spots, dross inclusions, zinc runs, and acid stains per IS 2629. Ask for photo documentation of sample galvanized members. | IS 2629 §7 | Medium
14 |  | Galvanizing after fabrication | CRITICAL: Specify that ALL fabrication (cutting, drilling, welding) must be completed BEFORE galvanizing. No cutting or drilling after galvanizing. Any post-galvanizing modification requires zinc-rich paint repair. | IS 2629 / Industry Practice | Critical
1 | 6. Painting & Aviation Marking | Aviation band painting specification | Specify: Alternate bands of international orange (IS 5 — Shade 597) and white (IS 5 — Shade 631) per AAI/DGCA requirements. Band width: 6m for 120m mast (approximately 20 bands total). | AAI NOC Conditions / ICAO Annex 14 | Critical
2 |  | Paint system for aviation bands | Specify: Primer — zinc chromate primer (1 coat, 35 microns DFT); Intermediate — epoxy micaceous iron oxide (2 coats, 100 microns DFT); Finish — synthetic enamel PU (2 coats, 40 microns DFT). Total DFT: 175 microns over galvanized surface. | IS 1477 / IS 2074 / MORTH Spec | High
3 |  | Surface preparation for painting | Ask: How is surface prepared for painting over galvanizing? Must use sweep blasting (aluminum oxide, 0.3-0.5 bar pressure) or etch primer per IS 1477. Direct paint on fresh galvanizing will peel. | IS 1477 / SSPC SP 16 | High
4 |  | Paint manufacturer | Ask: Which paint manufacturer? Specify approved brands: Asian Paints, Berger, Nippon, or Jotun. Ask for paint technical data sheets and compatibility with galvanized surface. | Industry Practice | Medium
5 |  | Dry Film Thickness (DFT) measurement | Ask: Will DFT be measured per coat? Specify DFT measurement with electronic gauge per IS 5665 at point of manufacture and after erection. Minimum 5 readings per 10 m². | IS 5665 / ISO 19840 | High
6 |  | Aviation warning light type | Specify: Low-intensity Type A red flashing light per ICAO Annex 14, Chapter 6. Minimum 2 lights (top + 60m level). Flash rate: 60-90 flashes per minute. Peak intensity: ≥ 10 cd. | ICAO Annex 14 / DGCA CAR Section 8 | Critical
7 |  | Aviation light power supply | Ask: Is the aviation light solar-powered? Specify: Solar panel + battery backup for minimum 48 hours continuous operation. Battery must be maintenance-free VRLA type. Ask for battery capacity calculation. | Industry Practice | High
8 |  | Aviation light compliance certificate | Require: Type test certificate for aviation light from DGCA-approved lab. Light must meet ICAO Annex 14 Type A specifications. Ask for certificate copy. | ICAO Annex 14 / DGCA | Critical
1 | 7. Corrosion Protection & Durability | Corrosivity category | Ask: What atmospheric corrosivity category is the mast designed for? Per IS 11724 / ISO 9223, specify Category C3 (moderate) for Tirunelveli inland or Category C4 (high) if within 5 km of coast. Our site is ~40 km from coast — C3 is adequate. | IS 11724 / ISO 9223 | High
2 |  | Salt spray test | Ask: Has the galvanizing been salt spray tested per IS 9844 / ASTM B117? For C3 environment, galvanized coating should pass minimum 1000 hours salt spray test without red rust. Ask for test certificates. | IS 9844 / ASTM B117 | High
3 |  | Coating life expectancy | Ask: What is the estimated time to first maintenance for the galvanized coating? Per IS 2629 / ISO 9224: for C3 environment, 86-micron galvanizing should last 20-25 years to first maintenance. Vendor to confirm. | ISO 9224 / IS 2629 | High
4 |  | Touch-up procedure for transit damage | Ask: What is the procedure for touch-up of galvanizing damaged during transport/erection? Must use zinc-rich paint (92% zinc in dry film, per IS 2629) or zinc-alloy solder. Minimum 2 coats. Vendor to provide repair kit. | IS 2629 §6 | High
5 |  | Bolt galvanizing | Specify: ALL bolts, nuts, and washers must be hot-dip galvanized per IS 1363 Part 3. No black bolts. Nuts must be oversize tapped after galvanizing. Ask for galvanizing certificates for fasteners. | IS 1363 Part 3 / IS 2629 | Critical
6 |  | Guy wire corrosion protection | Ask: Are guy wires galvanized? Specify: Guy wire rope must be galvanized per IS 2266 Class A (heaviest coating). Ask for galvanizing class certificate from wire rope manufacturer. | IS 2266 | Critical
7 |  | Dissimilar metal isolation | Ask: Are dissimilar metals isolated? Stainless steel and galvanized steel in contact cause galvanic corrosion. Ask for isolation details (neoprene washers, nylon sleeves) at all stainless-to-galvanized interfaces. | IS 11724 / Industry Practice | Medium
8 |  | Water entrapment prevention | Ask: Are structural member orientations designed to prevent water entrapment? Angles should be oriented with horizontal leg facing down (tubular members should have drain holes). Ask for orientation drawing. | IS 2629 / Industry Practice | High
9 |  | Sealant at joints | Ask: Are bolted joints sealed with mastic or sealant to prevent crevice corrosion? Specify: All site bolted connections must receive bead of butyl mastic sealant after torque check. | Industry Practice | Medium
1 | 8. Bolting & Fasteners | Bolt grade | Specify: All structural bolts must be HSFG Grade 8.8 per IS 1363 Part 1 as minimum. For critical connections (base plate, guy attachments), use Grade 10.9. Ask for bolt test certificates per IS 1363. | IS 1363 Part 1 / IS 4000 | Critical
2 |  | Bolt diameter | Ask: What bolt diameters are used? Typical: M16 for bracing connections, M20/M24 for main leg splices, M30/M36 for base plate. Ask for bolt schedule with sizes, grades, and quantities. | IS 800 / IS 4000 | High
3 |  | Nut specification | Specify: Nuts per IS 1363 Part 2, Grade 8 or 10 matching bolt grade. Must be oversize tapped after galvanizing per IS 1363 Part 3. Ask for nut test certificates. | IS 1363 Part 2 & 3 | Critical
4 |  | Washer specification | Specify: Hardened flat washers per IS 2016, galvanized. Spring washers per IS 3063 for vibration-prone connections. Ask for washer specification and quantity. | IS 2016 / IS 3063 | High
5 |  | Torque specification | Ask: What is the required torque for each bolt size? Per IS 4000, typical: M16 = 135 Nm, M20 = 260 Nm, M24 = 450 Nm. Ask for torque specification table and require torque wrench calibration certificates. | IS 4000 | Critical
6 |  | Torque verification | Require: All HSFG bolted connections must be torque-verified after erection using calibrated torque wrench. Provide torque verification report for each connection. Random check: minimum 10% of bolts. | IS 4000 / Industry Practice | Critical
7 |  | Anti-vibration measures | Ask: Are anti-vibration measures provided? Specify: Nyloc nuts or double nuts with spring washers on all vibrating connections. Wire locking on critical guy wire attachments. Ask for anti-vibration fastener details. | Industry Practice | High
8 |  | Bolt quantity and BOM | Ask: Does vendor provide complete Bill of Materials (BOM) with bolt counts for each size, grade, and location? Essential for site inventory and QC. Ask for BOM with 5% spares. | Industry Practice | High
1 | 9. Welding (Shop Fabrication) | Welding standard | Specify: All shop welding per IS 816 or AWS D1.1. No site welding allowed — all welding in controlled factory environment. Ask for Welding Procedure Specifications (WPS). | IS 816 / AWS D1.1 | Critical
2 |  | Welder qualification | Ask: Are all welders qualified per IS 817 or AWS D1.1? Require welder qualification test certificates. Each welder must have valid qualification for the joint type and position. | IS 817 / AWS D1.1 | Critical
3 |  | Weld type | Ask: What weld types are used? Fillet welds for angle-to-gusset connections. Partial penetration welds for base plate. Ask for weld size verification — minimum leg length per IS 816. | IS 816 / IS 800 | High
4 |  | Weld inspection | Ask: What NDT is performed on welds? Specify: 100% visual inspection per IS 8174, 10% MT/PT for fillet welds, 100% UT for butt welds. Ask for NDT reports from certified inspector. | IS 8174 / IS 9595 / IS 13886 | High
5 |  | Weld quality acceptance | Specify: No cracks, porosity, undercut, spatter, or incomplete penetration acceptable. All welds must meet IS 8174 acceptance criteria. Ask for weld inspection reports with photographs. | IS 8174 | High
6 |  | Weld repair procedure | Ask: What is the weld repair procedure? Defective welds must be gouged out and re-welded per approved WPS. Maximum 2 repairs per joint. Ask for repair procedure documentation. | IS 816 / AWS D1.1 | Medium
1 | 10. Foundation Design | Foundation type | Ask: What foundation type is proposed? For guyed mast: typically reinforced concrete block foundation at base + separate guy anchor blocks. For 120m guyed mast: base block approx 2.5m × 2.5m × 2.0m, each guy anchor approx 1.5m × 1.5m × 1.2m. | IS 1904 / IS 456 | Critical
2 |  | Concrete grade | Specify: Minimum M25 grade concrete per IS 456 for all foundations. M30 for guy anchor blocks in aggressive soil. Ask for concrete mix design and cube test results (28-day strength). | IS 456 | Critical
3 |  | Reinforcement steel | Specify: Fe 500D TMT bars per IS 1786. Minimum reinforcement: 0.25% of cross-section for columns, 0.2% for footings per IS 456. Ask for bar bending schedule. | IS 1786 / IS 456 | Critical
4 |  | Anchor bolt embedment | Ask: What is the anchor bolt embedment length in concrete? Per IS 456, minimum embedment = 40× bolt diameter for hooked anchors. For M30: minimum 1200mm embedment. Ask for pull-out calculation. | IS 456 | Critical
5 |  | Soil parameters assumed | Ask: What soil parameters does the vendor assume for foundation design? For our site: SBC = 150 kN/m², water table = 5m BGL, soil type = medium clay / weathered rock. Vendor must confirm foundation design for these parameters. | IS 1904 / IS 6403 | Critical
6 |  | Foundation design report | Require: Complete foundation design report with SBC verification, overturning check, sliding check, pull-out check for guy anchors, and settlement analysis. Signed by qualified structural engineer. | IS 1904 / IS 456 | Critical
7 |  | Backfill specification | Ask: What is the backfill specification? Specify: Backfill with selected excavated soil in 200mm layers, compacted to 95% MDD per IS 2720 Part 8. Guy anchor backfill is critical — ask for compaction test procedure. | IS 2720 / IS 1904 | High
1 | 11. Erection & Commissioning | Erection method | Ask: What is the erection method? For 120m guyed lattice: gin pole method is standard. Crane is rarely feasible for 120m height. Ask for step-by-step erection procedure with sequence drawings. | Industry Practice | Critical
2 |  | Erection duration | Ask: What is the estimated erection duration? Typical: 5-7 days for 120m guyed mast with 6-person crew. Ask for detailed erection schedule including weather contingency. | Industry Practice | High
3 |  | Crew qualification | Ask: Are erectors certified and experienced? Require: minimum 3 similar mast erections in last 5 years. Ask for crew CV/experience certificates. At least 1 rigger with valid certification. | Industry Practice | High
4 |  | HSE plan | Require: Complete HSE plan including risk assessment, fall protection (100% tie-off above 2m), emergency rescue plan, first aid, communication protocol. Ask for HSE plan document before mobilization. | IS 7205 / Factories Act 1948 | Critical
5 |  | Fall protection system | Ask: Is a permanent fall protection system (climbing ladder with safety cable / rail) included? Specify: continuous fall protection per IS 7205 from 2m to top. Ask for system manufacturer and certification. | IS 7205 / OSHA 1926 Subpart M | Critical
6 |  | Climbing ladder | Ask: Is a climbing ladder included? Specify: internal or external climbing ladder with rest platforms every 10m per IS 7205. Ladder rungs: 300mm spacing, 300mm clearance behind rung. | IS 7205 | High
7 |  | Rest platforms | Ask: Are rest platforms provided? Specify: minimum 1 rest platform every 10m per IS 7205. Each platform: 600mm × 600mm minimum with safety rail. | IS 7205 | High
8 |  | Guy wire tensioning after erection | Require: Guy wire pre-tension to be checked and adjusted after full erection. Record tensions using calibrated load cell. Re-check after 1 month and 6 months. Ask for tensioning procedure. | Industry Practice | Critical
9 |  | Plumb check | Require: Mast verticality to be checked after erection. Tolerance: ±1:500 of height (240mm for 120m). Ask for plumb survey report using total station or theodolite. | Industry Practice | High
10 |  | Erection completion certificate | Require: Signed erection completion certificate confirming all members installed, all bolts torqued, guy tensions set, plumb verified, lightning protection connected, aviation lights operational. | Industry Practice | Critical
1 | 12. Lightning Protection | LPS design standard | Specify: Lightning Protection System per IEC 62305 Level III (for Tamil Nadu with 20-30 thunderstorm days/year). Ask for LPS design calculations including rolling sphere method for air terminal placement. | IEC 62305-1 / IS 2309 | Critical
2 |  | Air terminal type | Ask: What air terminal is provided? Specify: Franklin rod or ESE (Early Streamer Emission) type at mast top. Minimum 1m above top anemometer. Ask for type test certificate. | IEC 62305 / IS 2309 | Critical
3 |  | Down conductors | Specify: Minimum 2 down conductors from top to grounding system per IEC 62305. Conductors bonded to mast structure at top, middle, and bottom. Copper conductor minimum 50mm² cross-section per IS 2309. | IEC 62305-3 / IS 2309 | Critical
4 |  | Grounding system | Specify: Ring earth electrode (minimum 50mm² copper) with ground rods (minimum 3m deep, copper-bonded steel) at each corner. Ground resistance must be less than 10 ohms per IEC 62305. Ask for grounding design. | IEC 62305-3 / IS 2309 | Critical
5 |  | Grounding resistance test | Require: Fall-of-potential method ground resistance test per IS 9226 after installation. Must achieve less than 10 ohms. If higher, additional ground rods required. Ask for test report format. | IS 9226 / IEC 62305-3 | Critical
6 |  | Surge protection on sensor cables | Specify: SPDs (Surge Protective Devices) on ALL sensor signal cables at the data logger enclosure. Type 2 SPDs per IEC 61643. Ask for SPD specifications and installation details. | IEC 62305-4 / IEC 61643 | High
7 |  | Equipotential bonding | Ask: Is equipotential bonding provided? All metallic parts (mast, guy wires, logger enclosure, solar panel frame) must be bonded to grounding system per IEC 62305-4. Ask for bonding detail drawing. | IEC 62305-4 / IS 2309 | High
1 | 13. Packing, Transport & Handling | Packing method | Ask: How are galvanized members packed for transport? Specify: members wrapped in VCI (Volatile Corrosion Inhibitor) paper, bundled with nylon straps (not wire, which damages galvanizing). Small parts in wooden crates. | Industry Practice | High
2 |  | Transport damage prevention | Ask: What measures prevent transport damage? Specify: timber dunnage between layers, no metal-to-metal contact, no dragging. Ask for packing and handling procedure document. | Industry Practice | High
3 |  | Storage at site | Ask: What are site storage requirements? Specify: members stored on timber skids minimum 150mm above ground, under tarpaulin cover, with VCI paper. No direct ground contact. Ask for storage procedure. | IS 2629 / Industry Practice | High
4 |  | Transport to site | Ask: Can vendor arrange transport to Tirunelveli site? If yes, ask for transport cost and delivery schedule. Typical: 2-3 truckloads for 120m guyed mast. Maximum member length: 6m (for road transport). | Industry Practice | Medium
5 |  | Handling equipment | Ask: What handling equipment is needed at site? Specify: crane or excavator for unloading (2-3 ton capacity), storage area 20m × 10m minimum. Ask for site preparation requirements. | Industry Practice | Medium
1 | 14. Quality Assurance & Documentation | QA plan | Ask: Does vendor have a documented Quality Assurance Plan? Require: QAP covering incoming material inspection, in-process inspection, final inspection, and NDT. Ask for QAP document. | ISO 9001 / Industry Practice | Critical
2 |  | Material traceability | Ask: Is material traceability maintained? Require: Heat numbers on all steel members traceable to mill test certificates. Marking per IS 2062. Ask for traceability procedure. | IS 2062 / ISO 9001 | Critical
3 |  | Third-party inspection | Require: Third-party inspection at fabrication stage by agency like SGS, TUV, Bureau Veritas, or Engineers India. Inspection stages: (1) raw material, (2) during fabrication, (3) after galvanizing, (4) packing. Ask for TPI scope. | Industry Practice | Critical
4 |  | Fabrication tolerance | Ask: What fabrication tolerances are maintained? Per IS 7215: member length ±2mm, hole position ±1mm, straightness L/1000. Ask for tolerance specification sheet. | IS 7215 / IS 800 | High
5 |  | Mill test certificates | Require: Mill test certificates per IS 2062 for ALL steel used — including chemical composition and mechanical properties (yield strength, UTS, elongation). Must be from steel manufacturer, not trader. | IS 2062 | Critical
6 |  | Document submission list | Require complete document package: (1) Structural design calculations, (2) Fabrication drawings, (3) Mill test certificates, (4) Galvanizing test certificates, (5) Welding WPS & welder qualifications, (6) NDT reports, (7) Bolt test certificates, (8) Guy wire test certificates, (9) Foundation design report, (10) Erection manual, (11) O&M manual, (12) Warranty certificates. | Industry Practice | Critical
1 | 15. Warranty & After-Sales Support | Structural warranty period | Specify: Minimum 15-year warranty against structural defects, corrosion failure, and manufacturing defects. Warranty must cover both material and workmanship. Ask for warranty terms and conditions. | Industry Practice | High
2 |  | Warranty exclusions | Ask: What is excluded from warranty? Typical exclusions: damage from unauthorized modification, extreme weather beyond design, third-party damage. Ensure galvanizing failure and weld defects are NOT excluded. | Industry Practice | High
3 |  | Annual inspection service | Ask: Does vendor offer annual inspection service? Recommend: annual inspection including guy wire tension check, bolt torque verification, corrosion assessment, plumb check. Ask for AMC terms. | Industry Practice | Medium
4 |  | Spare parts supply | Ask: What spare parts are supplied? Specify: 2% spare galvanized members (angles, gussets), 5% spare bolts/nuts/washers per size, spare guy wire sections. Ask for spares list. | Industry Practice | High
5 |  | Emergency support | Ask: What is the emergency response capability? If mast is damaged by cyclone, what is the vendor's response time? Ask for emergency contact and mobilization timeline. | Industry Practice | Medium
1 | 16. Cost & Commercial Terms | Quotation basis | Ask: Is the quote on FOR site basis or ex-works? Require: FOR site (Tirunelveli) including transport, unloading, erection, and commissioning. No hidden costs for transport or logistics. | Industry Practice | Critical
2 |  | Scope inclusions | Ask: Confirm scope includes: mast structure, all galvanizing, painting, aviation lights, climbing ladder, fall protection, lightning protection, boom mounting brackets at specified heights, guy wires, anchors, foundation design, erection, commissioning. | Industry Practice | Critical
3 |  | Scope exclusions | Ask: What is explicitly excluded? Typically: foundation construction (civil work), instrumentation, data logger, site preparation, approach road. Ensure clarity on what is in vs out of scope. | Industry Practice | Critical
4 |  | Payment terms | Ask: What are the payment terms? Industry standard: 20% advance, 50% on dispatch, 25% on erection completion, 5% retention (released after 12 months). Negotiate retention release terms. | Industry Practice | High
5 |  | Delivery schedule | Ask: What is the guaranteed delivery schedule? Require: delivery within 10 weeks from PO. Include liquidated damages clause for delay (typically 0.5% per week, max 5%). | Industry Practice | High
6 |  | Performance guarantee | Ask: Is there a performance guarantee? Specify: mast must survive design wind speed without permanent deformation for 20 years. Ask for performance guarantee terms and conditions. | Industry Practice | High

## Instrumentation
Instrumentation — Procurement Checklist
# | Category | Item | What to Ask / Specify | Standard / Reference | Priority | Vendor Response | Compliant? | Remarks
1 | 1. Anemometers (Wind Speed) | Sensor type & class | Specify: Class 1 cup anemometer per IEC 61400-12-1. Approved models: Thies First Class (4.3351.x0.xxx), Riso P2546A, or Vector A100LK. Class 2 is NOT acceptable for hub-height measurement. | IEC 61400-12-1 Annex F | Critical
2 |  | Quantity and placement | Specify: Minimum 6 anemometers — 2 per height level × 3 heights (120m, 60m, 30m). Layout: 1 top-mounted at 120m apex + 1 side-mounted at each height on dedicated booms. | IEC 61400-12-1 §5.2 | Critical
3 |  | Height levels | Specify: Level 1 = 120m (hub height), Level 2 = 58m (mid-height), Level 3 = 30m (low level). Heights must be exact — even 0.5m deviation affects vertical extrapolation. | IEC 61400-12-1 / IEA Recommendations | Critical
4 |  | MEASNET calibration | Require: Each anemometer MUST have individual MEASNET-traceable wind tunnel calibration certificate. Calibration must be from an accredited lab (e.g., Deutsche WindGuard, SOH, WindSpace). Non-MEASNET calibration is NOT acceptable for bankable measurements. | MEASNET / IEC 61400-12-1 §5.3.2 | Critical
5 |  | Calibration uncertainty | Ask: What is the stated calibration uncertainty? Must be < 1% of reading (typically 0.5-0.8% for Class 1). Ask for uncertainty budget from calibration lab. | MEASNET / IEC 61400-12-1 | Critical
6 |  | Calibration date | Require: Calibration certificate must be less than 24 months old at time of installation. Anemometers older than this must be recalibrated before deployment. Ask for certificate dates. | IEC 61400-12-1 | High
7 |  | Top-mounted anemometer | Specify: 1 anemometer must be top-mounted on a dedicated pole at the mast apex (above all guy wires and aviation light). This avoids tower shadow completely. Ask for top pole design. | IEC 61400-12-1 §5.3.4 | Critical
8 |  | Boom mounting specification | Specify: Side-mounted anemometers on booms projecting minimum 6× the mast face width from mast center. For 1.2m face: minimum boom length = 7.2m (use 8m boom). Ask for boom design drawing. | IEC 61400-12-1 §5.3.5 | Critical
9 |  | Boom orientation | Specify: Boom orientation must minimize tower shadow for prevailing wind directions. For Tirunelveli (prevailing SW/NE winds): booms at 315° and 135° (perpendicular to prevailing winds). Ask for orientation justification. | IEC 61400-12-1 §5.3.5 | High
10 |  | Tower shadow correction | Require: Vendor must provide tower shadow correction methodology — either from wind tunnel tests on the specific mast cross-section or using IEC 61400-12-1 Annex G formulas. Ask for correction coefficients. | IEC 61400-12-1 Annex G | Critical
11 |  | Anemometer mounting detail | Ask: How is the anemometer mounted on the boom? Must use manufacturer-approved mounting bracket with proper alignment. Anemometer shaft must be vertical within ±1°. Ask for mounting detail drawing. | IEC 61400-12-1 §5.3 | High
12 |  | Overspeeding correction | Ask: Has overspeeding correction been considered? Cup anemometers tend to overestimate in turbulent flow. Class 1 anemometers have known overspeeding characteristics — ask for correction data. | IEC 61400-12-1 Annex F | Medium
1 | 2. Wind Vanes (Wind Direction) | Sensor type | Specify: Potentiometer or digital wind vane. Approved models: Thies Compact (4.3150.x0), NRG #200P, or Vector W200P. Ask for type selection justification. | IEC 61400-12-1 §5.4 | High
2 |  | Quantity and placement | Specify: Minimum 2 wind vanes — at 120m and 58m heights. Mount on dedicated booms (separate from anemometer booms) to avoid flow interference. Minimum 1m vertical separation from anemometer. | IEC 61400-12-1 §5.4 | High
3 |  | Dead band specification | Ask: What is the dead band of the vane? Must be < 5° (typically 1-3° for quality vanes). Dead band must be oriented away from prevailing wind directions. Ask for dead band orientation recommendation. | IEC 61400-12-1 §5.4 | High
4 |  | Direction calibration | Require: Each vane must have a direction calibration certificate confirming linearity and dead band. Calibration to be performed in controlled conditions. Ask for calibration method and certificate. | IEC 61400-12-1 | High
5 |  | Vane orientation procedure | Ask: What is the procedure for orienting the vane to true north? Must use survey-grade compass or GPS. Orientation error must be < 2°. Ask for orientation procedure and verification method. | IEC 61400-12-1 §5.4.3 | Critical
6 |  | Boom length for vanes | Specify: Vane boom length minimum 4× mast face width (shorter than anemometer boom is acceptable). For 1.2m face: minimum 4.8m boom. Ask for boom design. | IEC 61400-12-1 | High
1 | 3. Temperature Sensors | Sensor type | Specify: PT100 RTD or precision thermistor with radiation shield. Approved: NRG #110S with #RS-50 shield, Thies Pt100 with shield. Must be shielded from direct solar radiation. | IEC 61400-12-1 §5.5 | High
2 |  | Quantity and placement | Specify: Minimum 2 temperature sensors — at 120m (or near hub height) and at 3m AGL. The temperature gradient between these levels is critical for stability analysis and vertical extrapolation. | IEC 61400-12-1 §5.5 | High
3 |  | Accuracy requirement | Specify: Accuracy ±0.3°C or better over the operating range (-20°C to +60°C). Ask for calibration certificate with accuracy statement at multiple temperature points. | IEC 61400-12-1 | High
4 |  | Radiation shield | Require: ALL temperature sensors must be equipped with naturally-ventilated radiation shields (multi-plate type, e.g., NRG #RS-50 or Gill type). Without shields, solar heating causes 1-3°C positive bias. Ask for shield type. | IEC 61400-12-1 / WMO CIMO Guide | Critical
5 |  | Temperature calibration | Require: Calibration certificate per ITS-90 for PT100 sensors. Minimum 3-point calibration (0°C, 25°C, 50°C). Ask for calibration certificate and uncertainty statement. | ITS-90 / IEC 60751 | High
1 | 4. Barometric Pressure | Sensor type | Specify: Barometric pressure sensor with accuracy ±0.5 hPa or better. Approved: NRG BP20, Vaisala PTB330, or Setra 278. Mount in weatherproof enclosure at mast base. | IEC 61400-12-1 §5.6 | High
2 |  | Accuracy and range | Specify: Range 600-1100 hPa, accuracy ±0.5 hPa at 20°C. Must include temperature compensation. Ask for calibration certificate with traceability to national standards. | IEC 61400-12-1 | High
3 |  | Installation location | Specify: Sensor installed in weatherproof IP65 enclosure at mast base, with static pressure head (to avoid wind-induced pressure errors). Ask for installation detail. | Industry Practice | Medium
4 |  | Calibration certificate | Require: Calibration certificate traceable to NPL/NIST. Minimum 5-point calibration across operating range. Certificate less than 12 months old. | IEC 61400-12-1 | High
1 | 5. Relative Humidity | Sensor type | Specify: Capacitive RH sensor with accuracy ±3% RH. Approved: NRG #XH, Rotronic HC2, Vaisala HMP155. Mount in sheltered position with radiation shield. | Industry Best Practice | Medium
2 |  | Purpose | Explain: RH data is used for (1) air density correction (affects energy yield), (2) icing detection (RH > 95% + T < 0°C = icing risk), and (3) data quality checks. | Industry Best Practice | Medium
1 | 6. Data Logger & Communication | Data logger model | Specify: Industry-standard logger with IEC 61400-12-1 compliance. Approved: NRG SymphoniePRO, Ammonit Meteo-42, Campbell Scientific CR6, or Wicom Loggy-L. Ask for model comparison and recommendation. | IEC 61400-12-1 §6 | Critical
2 |  | Number of channels | Specify: Minimum 16 channels (6 anemometers + 2 vanes + 2 temp + 1 pressure + 1 RH + 1 rain + 1 spare counter + 2 spare analog). Ask for channel allocation plan. | IEC 61400-12-1 | Critical
3 |  | Sampling rate and averaging | Specify: Minimum 1 Hz sampling, 10-minute statistical output (mean, max, min, standard deviation) per IEC 61400-12-1. Ask for confirmation and specify no sub-sampling. | IEC 61400-12-1 §6.2-6.3 | Critical
4 |  | Data storage capacity | Specify: Minimum 6 months of data storage on SD card as backup (in case of communication failure). Ask for storage capacity calculation based on number of channels and logging interval. | Industry Best Practice | High
5 |  | GPS time synchronization | Require: GPS-synchronized clock for accurate timestamping. Clock drift must be < 10 seconds per month. GPS antenna must be installed with clear sky view. Ask for GPS sync specification. | IEC 61400-12-1 §6.2 | High
6 |  | 4G/LTE communication | Specify: Built-in 4G/LTE modem for daily data push to cloud/FTP server. Must support SMTP email and FTP/SFTP protocols. Ask for data push frequency and protocol details. | Industry Best Practice | High
7 |  | Satellite backup | Ask: Is satellite communication available as backup? For remote Indian sites with poor cellular coverage, Iridium or other satellite modem is essential. Ask for satellite communication option and cost. | Industry Best Practice | Medium
8 |  | Data format compatibility | Ask: What output data format is supported? Must be compatible with Windographer, WAsP, and standard analysis tools. Formats: RWD (NRG), SDAT (Ammonit), or standard CSV with headers. Ask for sample data file. | Industry Best Practice | High
9 |  | Remote diagnostics | Ask: Can the logger be remotely monitored and configured? Require: remote status check (battery voltage, sensor health, communication status) via web portal or email. Ask for remote access capability. | Industry Best Practice | Medium
10 |  | Power supply | Ask: What is the power supply? For 120m mast: solar panel (minimum 50W) + battery (minimum 40Ah) for logger + communication. Ask for power budget calculation including all sensors and modem. | Industry Best Practice | High
11 |  | Logger enclosure | Specify: IP65 weatherproof steel enclosure with lock, mounted at mast base (2-3m AGL). Must include DIN rail for SPDs, terminal blocks, and cable glands. Ask for enclosure specification. | IEC 60529 / Industry Practice | High
1 | 7. Booms & Mounting Hardware | Boom material | Specify: Hot-dip galvanized steel tube or angle, minimum 50mm diameter / 50×50×5 angle. Must be rigid enough to prevent vibration-induced anemometer errors. Ask for boom section specification. | IEC 61400-12-1 | High
2 |  | Boom length verification | Ask: Confirm boom length meets IEC requirement. For 1.2m face width mast: minimum 7.2m boom (6× face width). Use 8m booms for margin. Ask for boom length calculation. | IEC 61400-12-1 §5.3.5 | Critical
3 |  | Boom vibration damping | Ask: Are boom dampers provided? Boom vibration can cause anemometer measurement errors. Specify vibration dampers or guyed boom supports for booms > 5m. Ask for vibration analysis. | IEC 61400-12-1 | High
4 |  | Sensor cable routing | Ask: How are sensor cables routed? Specify: cables inside boom tube or in UV-resistant conduit along boom. No dangling cables. Cable glands at logger enclosure. Ask for cable routing detail. | Industry Practice | Medium
5 |  | Boom mounting bracket | Ask: What type of boom-to-mast bracket is used? Must be rigid, galvanized, and allow precise boom orientation. Ask for bracket design and orientation adjustment capability. | IEC 61400-12-1 | High
1 | 8. Calibration & Documentation | Anemometer calibration certificates | Require: Individual MEASNET-traceable wind tunnel calibration certificate for EACH anemometer. Certificate must include: calibration lab accreditation, calibration date, transfer function, uncertainty, and test points. | MEASNET / IEC 61400-12-1 | Critical
2 |  | Wind vane calibration certificates | Require: Direction calibration certificate for each wind vane including dead band measurement, linearity check, and orientation reference. Ask for calibration procedure documentation. | IEC 61400-12-1 | High
3 |  | Sensor serial number log | Require: Complete sensor serial number register mapping each sensor to its calibration certificate, mounting height, boom orientation, and data logger channel. Critical for data traceability. | IEC 61400-12-1 | Critical
4 |  | Sensor mounting verification | Require: Post-installation verification report confirming each sensor's height, orientation, boom length, and proximity to mast elements. Includes photographs of each sensor installation. | IEC 61400-12-1 | Critical
5 |  | Data recovery monitoring plan | Ask: What is the data recovery monitoring plan? Require: daily automated data quality check, weekly review of data recovery rates, monthly report. Target: ≥ 90% data recovery per IEC. | IEC 61400-12-1 / Industry Standard | High
6 |  | Recalibration schedule | Ask: What is the recalibration schedule for anemometers? MEASNET recommends recalibration after 2 years of operation. Ask vendor to include recalibration service in AMC. | MEASNET | Medium
1 | 9. Instrumentation Warranty & Spares | Instrumentation warranty | Specify: Minimum 2-year warranty for all sensors and data logger from date of commissioning. Warranty must cover manufacturing defects and calibration drift beyond specifications. | Industry Practice | High
2 |  | Spare sensors | Specify: Vendor must supply minimum 1 spare anemometer (pre-calibrated), 1 spare wind vane, and 1 spare temperature sensor. These must have calibration certificates. Ask for spares list and pricing. | Industry Practice | High
3 |  | Replacement lead time | Ask: What is the lead time for sensor replacement? Target: < 2 weeks for critical sensors (anemometers, vanes). Ask for emergency supply agreement. | Industry Practice | Medium
4 |  | AMC for instrumentation | Ask: Does vendor offer Annual Maintenance Contract for instrumentation? Specify: AMC includes sensor health check, recalibration scheduling, logger firmware updates, and technical support. | Industry Practice | Medium

## Vendor Evaluation
Vendor Evaluation Matrix — Mast + Instrumentation
# | Evaluation Criteria | Weight | Key Focus Area | Vendor A Score (1-10) | Vendor A Weighted | Vendor B Score (1-10) | Vendor B Weighted | Vendor C Score (1-10) | Vendor C Weighted
1 | Structural Design & Calculations | 15% | IS 875, IS 1893, BS EN 1993-3-1 compliance, design review
2 | Galvanizing & Corrosion Protection | 15% | IS 2629/2633 compliance, zinc thickness, certificates
3 | Welding & Fabrication Quality | 10% | IS 816/AWS D1.1, NDT, WPS, welder qualifications
4 | Bolting & Fasteners | 5% | HSFG bolts, IS 4000, torque specification
5 | Foundation Design | 10% | IS 456, IS 1904, site-specific design
6 | Lightning Protection | 5% | IEC 62305 compliance, grounding design
7 | Aviation Marking & Lighting | 5% | AAI/DGCA compliance, solar light
8 | Instrumentation & Calibration | 15% | IEC 61400-12-1, MEASNET, Class 1 anemometers
9 | Data Logger & Communication | 5% | 1 Hz sampling, GPS, 4G, data format
10 | Erection & Commissioning Capability | 5% | Crew experience, HSE plan, climbing safety
11 | Documentation & QA/QC | 5% | Mill certs, galv certs, WPS, NDT, traceability
12 | Warranty & After-Sales Support | 5% | 15yr structural, 2yr instrumentation, AMC
| TOTAL WEIGHTED SCORE | 100%
RECOMMENDED VENDOR:

## Document Checklist
Document Submission Checklist
# | Category | Document Required | Received? | Date Received | Verified? | Remarks
1 | Structural Design | Structural Design Calculations (IS 875-3, IS 1893, BS EN 1993-3-1)
2 | Structural Design | Foundation Design Report (IS 456, IS 1904) — site-specific for SBC 150 kN/m²
3 | Structural Design | Design Wind Speed Computation Sheet (IS 875-3 with K1, K2, K3, K4)
4 | Structural Design | Third-Party Structural Design Review Certificate
5 | Structural Design | Guy Wire Load Calculation & Safety Factor Verification
6 | Fabrication | Fabrication / Shop Drawings with all member sizes and connection details
7 | Fabrication | Bill of Materials (BOM) — structural steel, bolts, guy wires
8 | Fabrication | Section Orientation Drawing (preventing water entrapment)
9 | Fabrication | Welding Procedure Specifications (WPS) per IS 816 / AWS D1.1
10 | Fabrication | Welder Qualification Test Certificates per IS 817
11 | Fabrication | NDT Reports — visual (100%), MT/PT (10%), UT (butt welds)
12 | Fabrication | Fabrication Tolerance Report per IS 7215
13 | Steel & Materials | Mill Test Certificates for all structural steel (IS 2062 Grade E250)
14 | Steel & Materials | Bolt Test Certificates (IS 1363 Part 1 — Grade 8.8 / 10.9)
15 | Steel & Materials | Nut Test Certificates (IS 1363 Part 2)
16 | Steel & Materials | Guy Wire Test Certificate (IS 2266 — breaking load, galvanizing class)
17 | Steel & Materials | Turnbuckle Proof Load Certificate (IS 4211)
18 | Steel & Materials | Anchor Bolt Material Certificate
19 | Galvanizing | Galvanizing Test Certificates — zinc coating thickness per IS 2633
20 | Galvanizing | Adhesion Test Report per IS 2629
21 | Galvanizing | Uniformity Test (Preece Test) Report per IS 2633
22 | Galvanizing | Zinc Certificate of Conformity (IS 209 — Grade Zn 98)
23 | Galvanizing | Bolt/Nut Galvanizing Certificate (IS 1363 Part 3)
24 | Painting | Paint Technical Data Sheets (primer, intermediate, finish)
25 | Painting | DFT Measurement Report per IS 5665
26 | Painting | Aviation Band Painting Completion Certificate
27 | Lightning | Lightning Protection Design Report per IEC 62305 / IS 2309
28 | Lightning | Grounding Resistance Test Report per IS 9226 (< 10 ohms)
29 | Lightning | SPD Specifications and Installation Details (IEC 61643)
30 | Aviation | AAI/DGCA Aviation Clearance (NOC)
31 | Aviation | Aviation Light Type Test Certificate (ICAO Annex 14 Type A)
32 | Aviation | Aviation Light Installation & Function Test Certificate
33 | Instrumentation | Anemometer MEASNET Calibration Certificates (one per sensor)
34 | Instrumentation | Wind Vane Calibration Certificates
35 | Instrumentation | Temperature Sensor Calibration Certificates (ITS-90)
36 | Instrumentation | Barometric Pressure Sensor Calibration Certificate
37 | Instrumentation | Data Logger Channel Verification Report
38 | Instrumentation | Sensor Serial Number Register with mounting details
39 | Instrumentation | Post-Installation Sensor Verification Report with photographs
40 | Instrumentation | Tower Shadow Correction Data / Methodology
41 | Installation | Erection Manual with step-by-step procedure and safety plan
42 | Installation | HSE Plan & Risk Assessment
43 | Installation | Erection Completion Certificate
44 | Installation | Guy Wire Tension Test Report (load cell readings)
45 | Installation | Plumb Survey Report (verticality verification)
46 | Installation | Bolt Torque Verification Report (minimum 10% random check)
47 | Operation | Inspection & Maintenance Manual
48 | Operation | Sensor Replacement Procedure
49 | Operation | Annual Inspection Checklist
50 | Warranty | Structural Warranty Certificate (minimum 15 years)
51 | Warranty | Instrumentation Warranty Certificate (minimum 2 years)
52 | Warranty | Guy Wire Warranty Certificate
53 | Warranty | Aviation Light Warranty Certificate

## IEC Quick Reference
IEC 61400-12-1 Quick Reference
Topic | Requirement Summary | Reference
Measurement Heights | At or near hub height; minimum 3 levels recommended (hub height, mid-height, low level) | IEC 61400-12-1 §5.2
Anemometer Class | Class 1 cup anemometer for power performance and bankable resource assessment | IEC 61400-12-1 §5.3 / Annex F
Anemometer Calibration | Individual MEASNET-traceable wind tunnel calibration for each sensor | IEC 61400-12-1 §5.3.2
Redundant Anemometers | Minimum 2 anemometers per measurement height (primary + backup) | IEC 61400-12-1 §5.2
Top-Mount Anemometer | At least one top-mounted anemometer at mast apex (avoids tower shadow) | IEC 61400-12-1 §5.3.4
Boom Length | Minimum 6x mast face width from mast center to anemometer (8-12x preferred) | IEC 61400-12-1 §5.3.5
Boom Orientation | Booms oriented to minimize tower shadow for prevailing wind directions | IEC 61400-12-1 §5.3.5
Tower Shadow Correction | Correction must be applied for tower shadow effects on wind speed measurements | IEC 61400-12-1 Annex G
Wind Direction | At least 1 wind vane; 2 recommended at different heights with dead band < 5° | IEC 61400-12-1 §5.4
Temperature | Air temperature at hub height and near ground for gradient / stability analysis | IEC 61400-12-1 §5.5
Atmospheric Pressure | Barometric pressure measurement required for air density calculation | IEC 61400-12-1 §5.6
Sampling Rate | Minimum 1 Hz sampling frequency (no sub-sampling) | IEC 61400-12-1 §6.2
Averaging Period | 10-minute averaging period with mean, max, min, standard deviation statistics | IEC 61400-12-1 §6.3
Data Recovery | Minimum 90% data recovery over 12-month measurement period for bankability | Industry Standard
Mast Siting | Mast should represent turbine site conditions; avoid obstacles and wakes from other masts/turbines | IEC 61400-12-1 §5.1
Calibration Currency | Anemometer calibration less than 24 months old at time of deployment | MEASNET / IEC 61400-12-1